## AFI-MULE
序号 | 标签名称（属性在界面显示内容） | 任务 | 标签类型 （Data Type） | 上传内容 | 是否为必填项 | 示例 | 说明 | 开始周数 | 结束周数
1 | Advance Architecture Design | Input from PT and NVH (BP&PL, TPN&Snorkel Noise) | 文本/Text | PT SSTS, IDSR | YES |  |  | -230 | -220
|  | Tuning Volume Distribution/Pipe diameter definition | 文本/Text |  | YES |  |  | -220 | -210
|  | Routing | 文本/Text | packge checking report | YES |  |  | -230 | -210
|  | Define material and thickness | 文本/Text |  | YES |  |  | -230 | -220
|  | Fix piont definition | 文本/Text | fix point CAE report | YES |  |  | -230 | -220
|  | Initial CAE anaylsis | 文本/Text | NVH&Back Pressure CAE report | YES |  |  | -220 | -210
|  | DDR Prepare | 文本/Text | DDR report | YES |  |  | -210 | -205
|  | Review with BFO | YES/NO |  | YES |  |  | -205 | -205
2 | SOW for SSP if Necessary | Sourcing strategy definition | 文本/Text | Sourcing strategy | YES |  |  | -220 | -210
|  | Initial SSTS for SOW | 文本/Text | SSTS | YES |  |  | -204 | -197
|  | Review with BFO | YES/NO |  | YES |  |  | -196 | -196
|  | SOW Release | 日历 | SOW package | YES |  |  | -196 | -196
3 | Mid-Term DCS | Design optimized | 文本/Text |  | YES |  |  | -194 | -190
|  | BOM prepare | 文本/Text |  | YES |  |  | -190 | -189
|  | TCA from FD | 文本/Text |  | YES |  |  | -189 | -187
|  | DCS file prepare | 文本/Text | DCS report | YES |  |  | -190 | -187
|  | Review with BFO | YES/NO |  | YES |  |  | -186 | -186
4 | DFMEA1 | Set up DFMEA team | 文本/Text | clearance check results | YES |  |  | -195 | -191
|  | Down load the latest base DFMEA, study the failure mode in research database and mark which are related to this program | 文本/Text |  | YES |  |  | -190 | -187
|  | Review with BFO | YES/NO |  | YES |  |  | -186 | -186
|  | DFMEA G1 Submit | 日历 |  | YES |  |  | -185 | -185
5 | AC Review | Design optimized | 文本/Text |  | YES |  |  | -185 | -181
|  | BOM prepare | 文本/Text |  | YES |  |  | -181 | -180
|  | TCA from FD | 文本/Text |  | YES |  |  | -180 | -178
|  | DCS file prepare | 文本/Text |  | YES |  |  | -182 | -178
|  | Review with BFO | YES/NO |  | YES |  |  | -179 | -179
6 | SOR | Initial EWO to get all P/Ns for the package | 文本/Text |  | YES |  |  | -178 | -178
|  | Input requirements get align with each function group or got deviation approval | 文本/Text |  | YES |  |  | -190 | -175
|  | Initial SSTS | 文本/Text |  | YES |  |  | -178 | -172
|  | All the appendixes fulfilled | 文本/Text |  | YES |  |  | -178 | -172
|  | SOR Review with BFO before submit to eSOR or EP system | 文本/Text |  | YES |  |  | -171 | -171
|  | SOR Release | 日历 |  | YES |  |  | -170 | -170
7 | PR #1 | Program Review PRE VPI | 文本/Text |  | YES |  |  | -180 | -172
|  | Timing | 文本/Text |  | YES |  |  | -180 | -172
|  | System Design Review | 文本/Text |  | YES |  |  | -180 | -172
|  | Pre-VPI Parts List | 文本/Text |  | YES |  |  | -180 | -172
|  | Review of Imperatives | 文本/Text |  | YES |  |  | -180 | -172
|  | SSTS @ SOR Review - Use checklist | 文本/Text |  | YES |  |  | -180 | -172
|  | Program Knowledge Set / Best Practice Review | 文本/Text |  | YES |  |  | -180 | -172
|  | N&V Contenting Strategy | 文本/Text |  | YES |  |  | -180 | -172
|  | BOP Conformance | 文本/Text |  | YES |  |  | -180 | -172
|  | LADV Status | 文本/Text |  | YES |  |  | -180 | -172
|  | Service Strategy | 文本/Text |  | YES |  |  | -180 | -172
|  | Manufacturing Requirement (MR) Compliance Review | 文本/Text |  | YES |  |  | -180 | -172
|  | Manufacturing Ergonomics | 文本/Text |  | YES |  |  | -180 | -172
|  | Fastening - Manufacturing Review | 文本/Text |  | YES |  |  | -180 | -172
|  | Fastener Joint Analysis | 文本/Text |  | YES |  |  | -180 | -172
8 | DFMEA2 | Create DFMEA block diagram & Create Interface Item/Function Matrix | 文本/Text | clearance check results | YES |  |  | -150 | -146
|  | Review with BFO | YES/NO |  | YES |  |  | -145 | -145
|  | DFMEA G2 Submit | 日历 |  | YES |  |  | -144 | -144
9 | Bid List | Target date for purchase submit Bid List in EP system/or by other way | 日历 |  | YES |  |  | -170 | -166
|  | Review with BFO and EGM | YES/NO |  | YES |  |  | -166 | -166
|  | DRE response the bid list in EP system (Aprove, Need TA or Reject) | 日历 |  | YES |  |  | -166 | -166
10 | Technical Assessment | TR date and content informed supplier | 日历 |  | YES |  |  | -166 | -166
|  | Is there any experience on congener product? Who is your main customer? | 文本/Text |  | YES |  |  | -166 | -163
|  | Will this supplier be able to meet the program timing? | 文本/Text |  | YES |  |  | -166 | -163
|  | How about the supplier’s design capability? (design, analysis, validation, etc.) | 文本/Text |  | YES |  |  | -166 | -163
|  | How about the supplier’s manufacture capability? (fixture, process, equipment, etc.) | 文本/Text |  | YES |  |  | -166 | -163
|  | What is supplier’s commitment in providing the necessary resources (investment, manpower, equipment, location, raw materials, etc. ) to achieve the program timing? | 文本/Text |  | YES |  |  | -166 | -163
|  | What special training and specifically in what areas is needed by the supplier? | 文本/Text |  | YES |  |  | -166 | -163
|  | Does the supplier need help with raw materials or parts procurement? | 文本/Text |  | YES |  |  | -166 | -163
|  | Does the supplier need the assistance of a Global source? Joint Venture? License agreement? | 文本/Text |  | YES |  |  | -166 | -163
|  | Is there any other engineering cost? （ED&D cost） | 文本/Text |  | YES |  |  | -166 | -163
|  | Additional comments (special processes, products, expertise, etc.) | 文本/Text |  | YES |  |  | -166 | -163
|  | Tech review additional checklist | 文本/Text |  | YES |  |  | -166 | -163
|  | TA review result review with BFO, EGM, SM | YES/NO |  | YES |  |  | -162 | -162
|  | TA result submit | 日历 |  | YES |  |  | -162 | -162
11 | Sourcing Process | Verify the sourcing ECD from purchase | 日历 |  | YES |  |  | -161 | -161
|  | 1st round quotation information(quotation, time plan) | 文本/Text |  | YES |  |  | -158 | -158
|  | 2nd round quotation information(quotation, time plan) | 文本/Text |  | YES |  |  | -155 | -155
|  | 3rd round quotation information(quotation, time plan), should be the last loop quotation | 文本/Text |  | YES |  |  | -152 | -152
|  | PSR | 日历 |  | YES |  |  | -149 | -149
|  | Nomination | 日历 |  | YES |  |  | -148 | -148
12 | DFMEA GR3 | Finalize DFMEA analysis with recommended actions | 文本/Text |  | YES |  |  | -160 | -155
|  | Define hign risk item and interface manufacture capability analysis. | 文本/Text |  | YES |  |  | -160 | -155
|  | Recommendation action and analysis items define. | 文本/Text |  | YES |  |  | -160 | -155
|  | Review meeting,get PDT member's comments and agreement | 文本/Text |  | YES |  |  | -160 | -155
|  | Review with BFO,lead engineer. | 文本/Text |  | YES |  |  | -155 | -155
|  | Archiving into GDM | 文本/Text |  | YES |  |  | -154 | -154
13 | Mule design | Package clearance checking | 文本/Text |  | YES |  |  | -152 | -148
|  | Performance checking | 文本/Text |  | YES |  |  | -152 | -148
|  | Design optimized | 文本/Text |  | YES |  |  | -152 | -148
|  | Interface checking | 文本/Text |  | YES |  |  | -147 | -147
|  | Review with BFO | YES/NO |  | YES |  |  | -147 | -147
14 | PR #2 | Program Review POST VPI | 文本/Text |  | YES |  |  | -149 | -145
|  | Timing | 文本/Text |  | YES |  |  | -149 | -145
|  | System Design Review | 文本/Text |  | YES |  |  | -149 | -145
|  | Review of Imperatives | 文本/Text |  | YES |  |  | -149 | -145
|  | SSTS @ SOR Review - Use checklist | 文本/Text |  | YES |  |  | -149 | -145
|  | Exhaust System Part Number Strategy | 文本/Text |  | YES |  |  | -149 | -145
|  | Hanger Interface Review | 文本/Text |  | YES |  |  | -149 | -145
|  | Program Knowledge Set / Best Practice Review | 文本/Text |  | YES |  |  | -149 | -145
|  | N&V Contenting Strategy | 文本/Text |  | YES |  |  | -149 | -145
|  | BOP Conformance | 文本/Text |  | YES |  |  | -149 | -145
|  | LADV Status | 文本/Text |  | YES |  |  | -149 | -145
|  | Service Strategy | 文本/Text |  | YES |  |  | -149 | -145
|  | Manufacturing Requirement (MR) Compliance Review | 文本/Text |  | YES |  |  | -149 | -145
|  | Manufacturing Ergonomics | 文本/Text |  | YES |  |  | -149 | -145
|  | Fastening - Manufacturing Review | 文本/Text |  | YES |  |  | -149 | -145
|  | Fastener Joint Analysis | 文本/Text |  | YES |  |  | -149 | -145
|  | KCDS/Traceability Requirements | 文本/Text |  | YES |  |  | -149 | -145
15 | Proto-tool for Mule | Timing review to define the TKO Date | 日历 |  | YES |  |  | -150 | -150
|  | Engineering design proposal review including drawing and math data,ensure they are meeting design requirement | 文本/Text |  | YES |  |  | -147 | -147
|  | Open issues in review meeting should list and follow up | 文本/Text |  | YES |  |  | -147 | -136
|  | Archiving the tooling check list into GDM | 文本/Text |  | YES |  |  | -147 | -136
|  | plan 1-2 visits to tooling supplier | YES/NO |  | YES |  |  | -147 | -136
|  | Tool finished | 日历 |  | YES |  |  | -136 | -136
16 | PPQP | Appearance check | 文本/Text |  | YES |  |  | -135 | -135
|  | Dimension check | 文本/Text |  | YES |  |  | -135 | -135
|  | Quality check | 文本/Text |  | YES |  |  | -135 | -134
|  | Performance check | 文本/Text |  | YES |  |  | -135 | -134
|  | Transportation package check | 文本/Text |  | YES |  |  | -134 | -134
|  | Document check and achieve | 文本/Text |  | YES |  |  | -134 | -134
|  | start date - end date | 日历 |  | YES |  |  | -134 | -134

## MULE-IV
序号 | 标签名称（属性在界面显示内容） | 任务 | 标签类型 （Data Type） | 上传内容 | 是否为必填项 | 示例 | 说明 | 开始周数 | 结束周数
1 | Tuning | Tuning plan and proposal review | 文本/Text |  | YES
|  | PT cal. Released | 文本/Text |  | YES
|  | booking vehicle | 文本/Text |  | YES
|  | PT cal. Engineer update cal. | 文本/Text |  | YES
|  | Road Load simulation | 文本/Text |  | YES
|  | Vehicle Contract/Documents Sign off | 文本/Text |  | YES
|  | 1st round tuning: Start Date-End Date | 文本/Text | NVH&Back Pressure CAE report | YES
|  | 2nd round tuning: Start Date-End Date | 文本/Text | NVH&Back Pressure CAE report | YES
|  | 3rd round tuning: Start Date-End Date | 文本/Text | NVH&Back Pressure CAE report | YES
2 | DFMEA GR3 | 1.Finalize DFMEA analysis with recommended actions | 文本/Text |  | YES
|  | 2.Define hign risk item and interface manufacture capability analysis. | 文本/Text |  | YES
|  | 3.Recommendation action and analysis items define. | 文本/Text |  | YES
|  | 4.Review meeting,get PDT member's comments and agreement | 文本/Text |  | YES
|  | 5.Review with BFO,lead engineer. | 文本/Text |  | YES
|  | 6.Archiving into GDM | 文本/Text |  | YES
3 | Peer Review 3 First Hardware | 1.Organize review meeting in EPRV system. | 文本/Text |  | YES
|  | 2.Final review before release to ensure all development and validation activites have been successfully | 文本/Text |  | YES
|  | 3.Open issue follow up review and ensure all be addressed | 文本/Text |  | YES
|  | 4.Review mule architecture subsystem test result,ensure they are reliable for tooling kick off | 文本/Text |  | YES
|  | 5.Program timing review | 文本/Text |  | YES
|  | 6.Tuning timing plan review based on regular suspension tuning timeline, and get agreement if any allowable timing change | 文本/Text |  | YES
|  | 7.Open issue list update base on new issue addition,achiving review result report into GDM 8.Feedback and close this review in E peer review system. | 文本/Text |  | YES
4 | DFMEA GR4 | 1.Make timing plan according to recooendation action and analysis list | 文本/Text |  | YES
|  | 2.RPN value redefine based on action and analysis list | 文本/Text |  | YES
|  | 3.Any new failure happen,need to update DFMEA. | 文本/Text |  | YES
|  | 4.Review and ensure some items which impact ME be transferred into PFMEA. | 文本/Text |  | YES
|  | 5.DRE should assure to initial the completed DFMEA/DRBFM analysis(does not include any columns under Action results heading) and pass approval process in GDM before GR4 deadline | 文本/Text |  | YES
|  | 6.SVE and EGM relative sign off persons in above approval process in GDM. | 文本/Text |  | YES
5 | SVER P2 | 1.P release EWO approval in CAB meeting | 文本/Text | EWO number | YES
|  | 2.Review and check design math data meet PATAC requirement(including layer setting,math data format,orientation,structure tree,material property and etc.refer to math data check list) | 文本/Text |  | YES
|  | 3.Review mathdata assembly and interface in latest,all EWO change be implemented | 文本/Text |  | YES
|  | 4.Assembly and temporary version release | 文本/Text |  | YES
|  | 5.IA update and temporary version release | 文本/Text |  | YES
6 | Soft Tooling | 1.Timing review to check TKO is meeting program MRD | 文本/Text |  | YES
|  | 2.EWO/Open issue list review,ensure no items which impact TKO action still open | 文本/Text |  | YES
|  | 3.No further EWOs be in draft phase | 文本/Text |  | YES
|  | 4.Engineering design proposal review including drawing and math data,ensure they are meeting design requirement | 文本/Text |  | YES
|  | 5.any open issues in review meeting should list and follow up | 文本/Text |  | YES
|  | 6.Archiving the tooling check list into GDM | 文本/Text |  | YES
|  | 7.plan 1-2 visits to tooling supplier. | 文本/Text |  | YES
7 | IV Parts Check | 1.BOM check to ensure PO release with latest right part number.BCR release if temporary BOM change be needed. | 文本/Text | clearance check results | YES
|  | 2.Use quality checklist to inspect parts | 文本/Text |  | YES
8 | DV Test | 1.Test sample review,pre-test DRBTR check per check list template.Critical area of welding part check and mark with white paint | 文本/Text |  | YES
|  | 2.Test status tracking in PDT,any crack need to record and update every day | 文本/Text |  | YES
|  | 3.Regular visual inspect:metal and welding seam crack,oil leakage,abnormal noise | 文本/Text |  | YES
|  | 4Test result review | 文本/Text |  | YES
|  | 5.After test,do DRBTR work per template list,meanwhile test sample sealin until SORP+1year. | 文本/Text |  | YES
9 | IV MRD | 1.Ensure DV test finished before IV sample delivery | 文本/Text |  | YES
|  | 2.BOM check to ensure PO release with latest right part number if EWO happen.BCR release if temporary BOM change be needed | 文本/Text |  | YES
|  | 3.PPQP two weeks ahead of MRD,Review PPQP document,specially tier 2 or 3 supllier list,ensure dimension is meeting over 98% eligible rate. | 文本/Text |  | YES
|  | 4.Any retrofit,need BSD support and make archiving | 文本/Text |  | YES
|  | 5.Review build SIL,follow up open issue list | 文本/Text |  | YES
|  | 6.Archiving SIL into GDM. | 文本/Text |  | YES