## auto_property
property | value
label | 258
bpmax | 200
bpmin | 20
ec | 2.0T
sorp | 2016-09-28

## auto_tags
Week | Date(Sorp-Week) | Date(Adjusted) | Update Program Milestone | Task | Task Duration(Week) | Task Start Time(Sorp-Week) | Task End Time(Start Time + Duration)
176 | 2013/5/15 | 2016-09-28 | Kick off
175 | 2013/5/22 |  |  | ${auto_task_0} | 3
174 | 2013/5/29
173 | 2013/6/5 |  |  | ${auto_task_1} | 4
172 | 2013/6/12
171 | 2013/6/19 |  |  | ${auto_task_2} | 5
170 | 2013/6/26
169 | 2013/7/3 |  |  | ${auto_task_3} | 6
168 | 2013/7/10
167 | 2013/7/17
166 | 2013/7/24
165 | 2013/7/31
164 | 2013/8/7
163 | 2013/8/14
162 | 2013/8/21 | 2016-09-10 | VVA_DSI
161 | 2013/8/28
160 | 2013/9/4 |  | DSI
159 | 2013/9/11
158 | 2013/9/18
157 | 2013/9/25
156 | 2013/10/2
155 | 2013/10/9
154 | 2013/10/16 |  | DTA
153 | 2013/10/23
152 | 2013/10/30
151 | 2013/11/6
150 | 2013/11/13
149 | 2013/11/20
148 | 2013/11/27
147 | 2013/12/4 |  | AD
146 | 2013/12/11
145 | 2013/12/18
144 | 2013/12/25
143 | 2014/1/1
142 | 2014/1/8
141 | 2014/1/15 |  | STD / VAVA
140 | 2014/1/22
139 | 2014/1/29
138 | 2014/2/5 |  | VPI
137 | 2014/2/12
136 | 2014/2/19 |  | STD MD
135 | 2014/2/26
134 | 2014/3/5
133 | 2014/3/12
132 | 2014/3/19
131 | 2014/3/26
130 | 2014/4/2
129 | 2014/4/9
128 | 2014/4/16
127 | 2014/4/23 |  | CVER LEV1
126 | 2014/4/30
125 | 2014/5/7
124 | 2014/5/14 |  | MRD RM_ BIW
123 | 2014/5/21
122 | 2014/5/28
121 | 2014/6/4 |  | ESO
120 | 2014/6/11 |  | MRD RM_ GA
119 | 2014/6/18
118 | 2014/6/25 |  | DSO
117 | 2014/7/2
116 | 2014/7/9 |  | FRMC
115 | 2014/7/16
114 | 2014/7/23 |  | CVER MMR /SVER LEV1
113 | 2014/7/30
112 | 2014/8/6
111 | 2014/8/13 |  | SF
110 | 2014/8/20
109 | 2014/8/27
108 | 2014/9/3
107 | 2014/9/10
106 | 2014/9/17
105 | 2014/9/24 |  | CVER / SVER MMR/IVER LEV1
104 | 2014/10/1
103 | 2014/10/8
102 | 2014/10/15
101 | 2014/10/22 |  | IDR
100 | 2014/10/29
99 | 2014/11/5
98 | 2014/11/12 |  | VSVA
97 | 2014/11/19
96 | 2014/11/26
95 | 2014/12/3
94 | 2014/12/10 |  | SVER/ IVER MMR
93 | 2014/12/17
92 | 2014/12/24 |  | VDR SM
91 | 2014/12/31
90 | 2015/1/7 |  | VDR EXT
89 | 2015/1/14
88 | 2015/1/21
87 | 2015/1/28
86 | 2015/2/4 |  | VDR/VIVA
85 | 2015/2/11
84 | 2015/2/18
83 | 2015/2/25
82 | 2015/3/4
81 | 2015/3/11 |  | MRD IV_ BIW
80 | 2015/3/18 |  | IVER
79 | 2015/3/25
78 | 2015/4/1
77 | 2015/4/8 |  | MRD IV_ GA
76 | 2015/4/15
75 | 2015/4/22
74 | 2015/4/29
73 | 2015/5/6 |  | FIVC
72 | 2015/5/13
71 | 2015/5/20
70 | 2015/5/27
69 | 2015/6/3
68 | 2015/6/10
67 | 2015/6/17
66 | 2015/6/24
65 | 2015/7/1 |  | 65% Cal. For IV Summer Test/IV Durability Test
64 | 2015/7/8
63 | 2015/7/15
62 | 2015/7/22
61 | 2015/7/29
60 | 2015/8/5
59 | 2015/8/12 |  | 65% Cal.
58 | 2015/8/19
57 | 2015/8/26
56 | 2015/9/2
55 | 2015/9/9
54 | 2015/9/16
53 | 2015/9/23 |  | 80cal for TA. / TA Emission Test
52 | 2015/9/30
51 | 2015/10/7
50 | 2015/10/14
49 | 2015/10/21
48 | 2015/10/28
47 | 2015/11/4
46 | 2015/11/11
45 | 2015/11/18 |  | IV Winter Test
44 | 2015/11/25 |  | 80% Cal.
43 | 2015/12/2
42 | 2015/12/9
41 | 2015/12/16
40 | 2015/12/23
39 | 2015/12/30
38 | 2016/1/6
37 | 2016/1/13
36 | 2016/1/20
35 | 2016/1/27
34 | 2016/2/3 |  | MRD PPV
33 | 2016/2/10
32 | 2016/2/17
31 | 2016/2/24
30 | 2016/3/2 |  | PPV
29 | 2016/3/9 |  | 99% Cal.
28 | 2016/3/16
27 | 2016/3/23
26 | 2016/3/30
25 | 2016/4/6 |  | CCC/TA CATALOG
24 | 2016/4/13
23 | 2016/4/20
22 | 2016/4/27
21 | 2016/5/4 |  | MVNS / 100% Cal.
20 | 2016/5/11
19 | 2016/5/18
18 | 2016/5/25
17 | 2016/6/1
16 | 2016/6/8
15 | 2016/6/15
14 | 2016/6/22 |  | PPAP
13 | 2016/6/29 |  | RPR Cal./BEIJING EMISSION
12 | 2016/7/6 |  | VDC
11 | 2016/7/13 |  | MVBS
10 | 2016/7/20
9 | 2016/7/27
8 | 2016/8/3
7 | 2016/8/10
6 | 2016/8/17
5 | 2016/8/24
4 | 2016/8/31
3 | 2016/9/7
2 | 2016/9/14
1 | 2016/9/21
0 | 2016/9/28 |  | SORP

## auto_task_0
property | value
label | Mule
desc | This is a Mule Task.
template | 3
snorkelNoiseXls | ${auto_snorkelnoise}

## auto_task_1
property | value
label | HotIssue
desc | This is a Hotissue Task.
template | 2
rootCause | what is the root cause?
solution | please give the solution
execute | details of execute
feedback | what about feedback?

## auto_task_2
property | value
label | EWO
desc | This is a EWO Task.
template | 1

## auto_task_3
property | value
label | Normal
desc | This is a Normal Task.
template | 0

## auto_snorkelnoise
| 3rd_Gear_WOT 2 | 3rd_Gear_WOT 2 | 3rd_Gear_WOT 2 | 3rd_Gear_WOT 2
| Snorkel | Snorkel | Snorkel | Snorkel
| OA-level | 2 order | 4 order | 6 order
| Snorkel | Snorkel | Snorkel | Snorkel
rpm | Pa | Pa | Pa | Pa
Linear | dB(A) | dB(A) | dB(A) | dB(A)
rpm | OA-level | 2 order | 4 order | 6 order
1000 | 66.7638 | 52.7443 | 51.7627 | 42.173
1020 | 67.1135 | 52.4167 | 52.8254 | 43.0791
1040 | 67.3909 | 52.4078 | 54.1837 | 43.0819
1060 | 67.6837 | 52.6473 | 55.8105 | 43.5354
1080 | 68.065 | 53.481 | 56.7424 | 44.0046
1100 | 68.4565 | 55.213 | 57.4946 | 44.9395
1120 | 68.7367 | 56.8627 | 57.7221 | 46.4346
1140 | 68.9052 | 57.8326 | 57.3316 | 47.7362
1160 | 69.0935 | 58.729 | 56.7228 | 48.9583
1180 | 69.3504 | 59.1216 | 56.2708 | 51.4897
1200 | 69.6317 | 59.1002 | 55.3978 | 51.5831
1220 | 69.8755 | 59.4006 | 54.7977 | 53.2785
1240 | 70.0486 | 59.4233 | 53.9882 | 54.0399
1260 | 70.1672 | 59.2403 | 53.0393 | 54.1653
1280 | 70.2409 | 59.7225 | 52.4363 | 55.149
1300 | 70.3598 | 60.4034 | 51.7254 | 54.6278
1320 | 70.6557 | 60.8954 | 50.7433 | 54.0797
1340 | 71.19 | 61.725 | 50.0566 | 54.2358
1360 | 71.9509 | 62.2929 | 49.348 | 54.3128
1380 | 72.7621 | 62.5146 | 48.6029 | 53.6373
1400 | 73.4938 | 63.0222 | 48.6605 | 53.4565
1420 | 74.0373 | 63.4447 | 49.3292 | 53.1288
1440 | 74.3808 | 63.7317 | 50.8689 | 52.8691
1460 | 74.5494 | 64.274 | 53.0939 | 53.1878
1480 | 74.595 | 64.8067 | 55.8521 | 53.4182
1500 | 74.6361 | 65.2911 | 57.662 | 53.9649
1520 | 74.7833 | 65.8804 | 59.094 | 53.7415
1540 | 75.0642 | 66.3407 | 60.5058 | 54.0615
1560 | 75.426 | 66.727 | 61.5666 | 54.1318
1580 | 75.7905 | 67.0891 | 62.2323 | 53.7745
1600 | 76.1265 | 67.5082 | 62.922 | 54.6206
1620 | 76.4756 | 67.9799 | 63.6686 | 55.1787
1640 | 76.9033 | 68.3674 | 64.2457 | 56.1809
1660 | 77.4464 | 68.7785 | 64.7571 | 56.2492
1680 | 77.9892 | 69.3341 | 65.3553 | 56.4774
1700 | 78.4607 | 69.6912 | 66.0648 | 57.2719
1720 | 78.7468 | 70.1104 | 66.7195 | 57.4834
1740 | 78.8535 | 70.6681 | 67.2807 | 58.0665
1760 | 78.8429 | 71.0211 | 67.8623 | 58.5091
1780 | 78.8177 | 71.5293 | 68.5229 | 59.1266
1800 | 78.8565 | 72.2472 | 69.2786 | 59.7818
1820 | 79.001 | 72.5649 | 69.6693 | 59.9344
1840 | 79.2403 | 73.087 | 70.1833 | 60.3626
1860 | 79.5634 | 73.8121 | 70.7089 | 60.9352
1880 | 79.9395 | 74.2376 | 70.9617 | 61.1964
1900 | 80.3329 | 74.7744 | 71.1988 | 61.936
1920 | 80.7248 | 75.3395 | 71.2579 | 62.3568
1940 | 81.1062 | 75.7211 | 71.2866 | 62.4282
1960 | 81.4987 | 76.1972 | 70.9832 | 62.327
1980 | 81.8812 | 76.7714 | 70.4615 | 62.3897
2000 | 82.2443 | 77.2444 | 69.8617 | 63.246
2020 | 82.54 | 77.613 | 69.2705 | 63.6061
2040 | 82.7406 | 78.0694 | 68.6727 | 63.7684
2060 | 82.8513 | 78.4564 | 67.9675 | 63.9094
2080 | 82.9052 | 78.8054 | 67.2482 | 64.5064
2100 | 82.9139 | 79.1375 | 66.5638 | 64.9622
2120 | 82.9074 | 79.408 | 65.8931 | 65.102
2140 | 82.9023 | 79.6787 | 65.1056 | 64.8917
2160 | 82.9196 | 79.9067 | 64.1037 | 63.971
2180 | 82.9772 | 80.123 | 63.096 | 63.6029
2200 | 83.0791 | 80.2958 | 62.0068 | 63.5856
2220 | 83.2065 | 80.3928 | 60.8981 | 63.0278
2240 | 83.3537 | 80.4983 | 59.6689 | 61.9489
2260 | 83.4891 | 80.6215 | 58.3951 | 60.7857
2280 | 83.5948 | 80.649 | 57.1789 | 59.1635
2300 | 83.6767 | 80.7522 | 55.7542 | 57.6685
2320 | 83.7528 | 80.8009 | 54.0086 | 56.8669
2340 | 83.843 | 80.8142 | 51.6399 | 57.7535
2360 | 83.9571 | 80.901 | 48.7895 | 59.5176
2380 | 84.0845 | 80.9677 | 44.0106 | 60.3521
2400 | 84.1953 | 80.9545 | 37.8017 | 60.6889
2420 | 84.2587 | 81.1279 | 40.7505 | 61.8563
2440 | 84.2742 | 81.1987 | 45.4232 | 62.8124
2460 | 84.2569 | 81.1702 | 47.5883 | 62.7055
2480 | 84.2314 | 81.3221 | 48.5265 | 63.2054
2500 | 84.2289 | 81.4015 | 49.597 | 64.7842
2520 | 84.2615 | 81.4092 | 51.1211 | 65.7538
2540 | 84.3169 | 81.5194 | 52.4392 | 66.1371
2560 | 84.3697 | 81.6074 | 53.2768 | 66.3824
2580 | 84.3989 | 81.6351 | 53.6766 | 66.8486
2600 | 84.4029 | 81.7235 | 54.1687 | 66.4213
2620 | 84.3849 | 81.755 | 54.9387 | 66.2224
2640 | 84.3534 | 81.7854 | 55.718 | 66.3708
2660 | 84.3147 | 81.8558 | 56.215 | 66.245
2680 | 84.269 | 81.8665 | 56.5184 | 66.3977
2700 | 84.2179 | 81.8737 | 56.3851 | 66.299
2720 | 84.1653 | 81.9117 | 55.9572 | 65.9694
2740 | 84.1185 | 81.9206 | 55.5923 | 65.5148
2760 | 84.0916 | 81.9063 | 55.5184 | 65.1165
2780 | 84.0944 | 81.9159 | 55.4221 | 65.113
2800 | 84.1208 | 81.9149 | 54.6783 | 64.7509
2820 | 84.1709 | 81.9567 | 54.211 | 64.3977
2840 | 84.2375 | 81.9899 | 54.1238 | 64.2429
2860 | 84.3189 | 82.0254 | 54.2629 | 64.3299
2880 | 84.4183 | 82.1185 | 54.4532 | 64.7766
2900 | 84.5351 | 82.1718 | 53.9794 | 65.1339
2920 | 84.6664 | 82.2685 | 53.3534 | 65.7111
2940 | 84.8064 | 82.3689 | 52.9972 | 66.5072
2960 | 84.9445 | 82.4295 | 53.1416 | 67.1442
2980 | 85.0764 | 82.5035 | 53.363 | 67.8513
3000 | 85.2048 | 82.6082 | 53.4367 | 68.5237
3020 | 85.3341 | 82.6258 | 53.7741 | 69.258
3040 | 85.4774 | 82.6506 | 54.3747 | 69.8226
3060 | 85.6407 | 82.7222 | 54.9164 | 70.2662
3080 | 85.8187 | 82.6714 | 55.4086 | 70.7755
3100 | 86.0082 | 82.6538 | 56.1122 | 71.2436
3120 | 86.2034 | 82.6757 | 56.214 | 71.8757
3140 | 86.4177 | 82.6169 | 56.4897 | 72.7998
3160 | 86.6501 | 82.628 | 55.9578 | 73.3937
3180 | 86.9021 | 82.697 | 54.6424 | 73.853
3200 | 87.1787 | 82.7294 | 53.4957 | 74.7172
3220 | 87.4463 | 82.7974 | 53.538 | 75.737
3240 | 87.703 | 82.9128 | 54.5242 | 76.6734
3260 | 87.9483 | 83.0061 | 56.1997 | 77.6076
3280 | 88.1973 | 83.1099 | 58.599 | 78.5929
3300 | 88.4685 | 83.2378 | 60.9035 | 79.5428
3320 | 88.7601 | 83.3645 | 62.892 | 80.2172
3340 | 89.0631 | 83.5059 | 64.7446 | 81.1771
3360 | 89.3491 | 83.6427 | 66.3215 | 81.9144
3380 | 89.5816 | 83.779 | 67.6592 | 82.5136
3400 | 89.7485 | 83.906 | 68.5493 | 82.9331
3420 | 89.8451 | 83.9992 | 69.1601 | 83.0043
3440 | 89.8971 | 84.1024 | 69.7074 | 83.011
3460 | 89.9205 | 84.1944 | 70.26 | 82.8718
3480 | 89.9332 | 84.2561 | 70.9737 | 82.6558
3500 | 89.9365 | 84.3373 | 71.6792 | 82.2833
3520 | 89.9266 | 84.4326 | 72.103 | 81.7634
3540 | 89.9021 | 84.4881 | 72.5775 | 81.4624
3560 | 89.8705 | 84.5557 | 73.2396 | 81.0405
3580 | 89.8448 | 84.6342 | 73.9677 | 80.3217
3600 | 89.8403 | 84.6733 | 74.5676 | 79.7444
3620 | 89.8531 | 84.7177 | 74.9805 | 79.2844
3640 | 89.8762 | 84.7638 | 75.2416 | 78.8899
3660 | 89.896 | 84.7579 | 75.5905 | 78.4093
3680 | 89.9085 | 84.7738 | 76.101 | 78.1187
3700 | 89.9238 | 84.7451 | 76.5597 | 77.9395
3720 | 89.9691 | 84.6799 | 76.9392 | 77.7677
3740 | 90.067 | 84.6299 | 77.3234 | 77.8304
3760 | 90.2278 | 84.5445 | 77.566 | 78.258
3780 | 90.4422 | 84.4449 | 77.8366 | 78.9047
3800 | 90.6912 | 84.3958 | 78.0907 | 79.6097
3820 | 90.9541 | 84.335 | 78.1587 | 80.308
3840 | 91.2093 | 84.2836 | 78.1622 | 80.7909
3860 | 91.4474 | 84.2673 | 78.1772 | 81.3072
3880 | 91.6691 | 84.218 | 78.1299 | 81.9222
3900 | 91.8719 | 84.1769 | 78.1466 | 82.6019
3920 | 92.0665 | 84.1674 | 78.2298 | 83.131
3940 | 92.2584 | 84.1554 | 78.1936 | 83.6723
3960 | 92.4457 | 84.1351 | 78.0491 | 84.0891
3980 | 92.6297 | 84.1206 | 77.6997 | 84.3887
4000 | 92.8177 | 84.0824 | 77.1296 | 84.5221
4020 | 93.0166 | 84.0333 | 76.775 | 84.6327
4040 | 93.2296 | 83.9791 | 76.7463 | 84.6779
4060 | 93.4424 | 83.9474 | 76.9005 | 84.6259
4080 | 93.6371 | 83.9395 | 77.0838 | 84.3969
4100 | 93.7815 | 83.9175 | 77.1627 | 84.1447
4120 | 93.8671 | 83.8883 | 77.1828 | 83.7175
4140 | 93.8929 | 83.8411 | 77.1704 | 83.0492
4160 | 93.8817 | 83.757 | 77.2035 | 82.2825
4180 | 93.855 | 83.6463 | 77.2713 | 81.4341
4200 | 93.8207 | 83.5316 | 77.2957 | 80.6415
4220 | 93.7824 | 83.4277 | 77.3094 | 79.9215
4240 | 93.7381 | 83.3332 | 77.3535 | 79.3105
4260 | 93.6819 | 83.2443 | 77.5214 | 78.7723
4280 | 93.6147 | 83.1242 | 77.6898 | 78.3133
4300 | 93.536 | 82.9902 | 77.7994 | 77.8525
4320 | 93.439 | 82.8186 | 78.0868 | 77.3934
4340 | 93.3346 | 82.6085 | 78.2857 | 76.6553
4360 | 93.2226 | 82.4011 | 78.5528 | 75.9261
4380 | 93.1143 | 82.2284 | 78.9114 | 75.2556
4400 | 93.015 | 82.0596 | 79.32 | 74.461
4420 | 92.9262 | 81.9296 | 79.7201 | 73.7315
4440 | 92.8719 | 81.84 | 80.1798 | 73.1353
4460 | 92.8722 | 81.7292 | 80.5921 | 72.6237
4480 | 92.9232 | 81.6194 | 81.0135 | 72.2851
4500 | 93.0202 | 81.508 | 81.4072 | 72.2833
4520 | 93.1523 | 81.3865 | 81.7415 | 72.553
4540 | 93.2989 | 81.2906 | 82.0558 | 73.04
4560 | 93.4433 | 81.218 | 82.2926 | 73.3851
4580 | 93.5788 | 81.1619 | 82.4828 | 73.5947
4600 | 93.6737 | 81.1044 | 82.6799 | 73.5678
4620 | 93.7059 | 81.019 | 82.8441 | 73.2341
4640 | 93.6579 | 80.9191 | 83.0901 | 72.8921
4660 | 93.5451 | 80.8046 | 83.2512 | 72.3262
4680 | 93.3905 | 80.6876 | 83.4394 | 71.7846
4700 | 93.2286 | 80.5737 | 83.6585 | 71.4041
4720 | 93.1014 | 80.4569 | 83.8874 | 71.4203
4740 | 93.0179 | 80.3606 | 84.2149 | 71.6802
4760 | 92.9825 | 80.304 | 84.525 | 72.1329
4780 | 92.9732 | 80.2589 | 84.8175 | 72.5018
4800 | 92.9841 | 80.2187 | 85.1106 | 72.8334
4820 | 93.0203 | 80.1912 | 85.3982 | 73.0345
4840 | 93.1038 | 80.1799 | 85.6623 | 73.2516
4860 | 93.2315 | 80.1703 | 85.9314 | 73.5561
4880 | 93.3869 | 80.1638 | 86.2175 | 73.7264
4900 | 93.5337 | 80.1456 | 86.4491 | 73.8228
4920 | 93.6634 | 80.1022 | 86.684 | 74.0482
4940 | 93.7718 | 80.0484 | 86.9111 | 74.3399
4960 | 93.881 | 79.9964 | 87.1619 | 74.8289
4980 | 93.9906 | 79.937 | 87.3448 | 75.2823
5000 | 94.0964 | 79.8768 | 87.5621 | 75.6388
5020 | 94.1977 | 79.8119 | 87.7758 | 76.0926
5040 | 94.2963 | 79.7663 | 88.0204 | 76.6973
5060 | 94.3974 | 79.7581 | 88.2021 | 77.3525
5080 | 94.492 | 79.7743 | 88.4081 | 78.1812
5100 | 94.5611 | 79.8113 | 88.5527 | 78.8797
5120 | 94.5984 | 79.8555 | 88.7033 | 79.4911
5140 | 94.5995 | 79.8726 | 88.8462 | 80.0195
5160 | 94.566 | 79.8425 | 88.9647 | 80.3928
5180 | 94.5039 | 79.7586 | 89.0828 | 80.6672
5200 | 94.4126 | 79.6307 | 89.1191 | 80.6758
5220 | 94.2901 | 79.4671 | 89.1524 | 80.5158
5240 | 94.1494 | 79.286 | 89.0977 | 80.1519
5260 | 94.0059 | 79.095 | 89.0108 | 79.8244
5280 | 93.8705 | 78.916 | 88.851 | 79.4707
5300 | 93.7581 | 78.807 | 88.6855 | 79.0142
5320 | 93.6744 | 78.7837 | 88.4857 | 78.307
5340 | 93.6225 | 78.8342 | 88.2935 | 77.5625
5360 | 93.5892 | 78.8913 | 88.113 | 76.8315
5380 | 93.545 | 78.9114 | 87.8994 | 76.3354
5400 | 93.4605 | 78.8932 | 87.7083 | 76.072
5420 | 93.3133 | 78.8447 | 87.4527 | 75.713
5440 | 93.1081 | 78.7935 | 87.2766 | 75.5102
5460 | 92.8946 | 78.74 | 87.1276 | 75.4435
5480 | 92.6986 | 78.6823 | 86.9512 | 75.5217
5500 | 92.5797 | 78.638 | 86.8262 | 75.9704
5520 | 92.5947 | 78.6531 | 86.7381 | 76.5452
5540 | 92.7471 | 78.754 | 86.6587 | 77.4016
5560 | 92.9807 | 78.9509 | 86.5881 | 78.2304
5580 | 93.2439 | 79.2088 | 86.5233 | 78.9785
5600 | 93.4941 | 79.4635 | 86.4304 | 79.7362

## README
sheet started with 'auto_' will be read automatically.
cell in this style ${auto_snorkelnoise} means 'please refer to auto_snorkelnoise sheet'

## MASTER TIMING
K226 Master Timing Chart-C15VVT
CAL YEAR | [12 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
MONTH | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M
Milestone
Product Engineering
Build
PT Cal
Ibooster&EBCM
Rear cradle
Exhaust/AIS
Fuel system
DSI
8/24
VPI
2/1
DSO
6/6
CSO
9/19
VDR
12/12
IVER
3/27
PPV
2/9
MVNS
4/16
MVBS
6/25
SORP
9/17
SVER
11/21
IVER LL
2/10
VSVA:
9/10
MRD RM_ GA
5/20
6/17
FRMC
MRD IV_ GA
3/24
4/24
FIVC
VTC
4/12
VVA_DSI:
7/27
VDC
5/21
50% Cal.
9/19
65% Cal.
7/31
100% Cal.
4/19
RPR Cal.
6/28
80% Cal.
12/4
99% Cal.
2/12
VVA_VPI:
11/28
VVA_CSO:
4/9
Kick off
1/7
DV Test
Mule sample
Dsign opimize
Mule tuning
Hard tooling
IV tuning
5/13
2/3
8/24
3/24
11/19
9/19
2/9
6/9
9/9
PV Test
4/9
1/24
Soft Tooling
Low U
Mule sample
Sourcing
design optimize & DIT
ABS
Final High U
7/15
High U/full regen
5/20
7/20
kick off
5/15
6/25
9/15
12/1
2/15
10/15
Final Low U
2/15
Final verification
3/15
kick off
SOR
Sourcing
SVER P2 DESIGN
IV Tooling
DV Test
Hard Tooling
PV TEST
8/6
10/12
1/6
9/15
12/20
3/20
9/14
2/2
TA+Sourcing
SOR
8/20
11/20
Soft tool
5/20
Lab test
Hard tooling
11/12
11/12
Hard tooling sample durability test
4/12
RLDA+Master table
8/20
6/25
Level 2
5/15
9/1
12/7
MOC
12/1
1/1

## template
template_id | template_label
3 | Mule
2 | HotIssue
1 | EWO
0 | 普通