## Sheet1
序号 | 标签名称（属性在界面显示内容） | 任务 | 标签类型 （Data Type） | 上传内容 | 是否为必填项 | 示例 | 说明 | 开始时间 | 结束时间
1 | Tuning | Tuning plan and proposal review | 文本/Text |  | YES |  |  | -114W | -113W
|  | PT cal. Released | 文本/Text |  | YES |  |  | -113W | -112W
|  | booking vehicle | 文本/Text |  | YES |  |  | -113W | -112W
|  | PT cal. Engineer update cal. | 文本/Text |  | YES |  |  | -113W | -112W
|  | Road Load simulation | 文本/Text |  | YES |  |  | -113W | -112W
|  | Vehicle Contract/Documents Sign off | 文本/Text |  | YES |  |  | -113W | -112W
|  | 1st round tuning: Start Date-End Date | 文本/Text | NVH&Back Pressure CAE report | YES |  |  | -112W | -110W
|  | 2nd round tuning: Start Date-End Date | 文本/Text | NVH&Back Pressure CAE report | YES |  |  | -109W | -107W
|  | 3rd round tuning: Start Date-End Date | 文本/Text | NVH&Back Pressure CAE report | YES |  |  | -106W | -104W
2 | DFMEA GR3 | 1.Finalize DFMEA analysis with recommended actions | 文本/Text |  | YES |  |  | -105W | -105W
|  | 2.Define hign risk item and interface manufacture capability analysis. | 文本/Text |  | YES |  |  | -105W | -105W
|  | 3.Recommendation action and analysis items define. | 文本/Text |  | YES |  |  | -105W | -105W
|  | 4.Review meeting,get PDT member's comments and agreement | 文本/Text |  | YES |  |  | -106W | -106W
|  | 5.Review with BFO,lead engineer. | 文本/Text |  | YES |  |  | -107W | -107W
|  | 6.Archiving into GDM | 文本/Text |  | YES |  |  | -109W | -109W
5 | SVER P2 | 1.P release EWO approval in CAB meeting | 文本/Text | EWO number | YES |  |  | -107W | -107W
|  | 2.Review and check design math data meet PATAC requirement(including layer setting,math data format,orientation,structure tree,material property and etc.refer to math data check list) | 文本/Text |  | YES |  |  | -107W | -107W
|  | 3.Review mathdata assembly and interface in latest,all EWO change be implemented | 文本/Text |  | YES |  |  | -107W | -107W
|  | 4.Assembly and temporary version release | 文本/Text |  | YES |  |  | -107W | -107W
|  | 5.IA update and temporary version release | 文本/Text |  | YES |  |  | -107W | -107W
3 | Peer Review 3 First Hardware | 1.Organize review meeting in EPRV system. | 文本/Text |  | YES |  |  | -115W | -115W
|  | 2.Final review before release to ensure all development and validation activites have been successfully | 文本/Text |  | YES |  |  | -115W | -115W
|  | 3.Open issue follow up review and ensure all be addressed | 文本/Text |  | YES |  |  | -115W | -115W
|  | 4.Review mule architecture subsystem test result,ensure they are reliable for tooling kick off | 文本/Text |  | YES |  |  | -115W | -115W
|  | 5.Program timing review | 文本/Text |  | YES |  |  | -115W | -115W
|  | 6.Tuning timing plan review based on regular suspension tuning timeline, and get agreement if any allowable timing change | 文本/Text |  | YES |  |  | -115W | -115W
|  | 7.Open issue list update base on new issue addition,achiving review result report into GDM 8.Feedback and close this review in E peer review system. | 文本/Text |  | YES |  |  | -115W | -115W
4 | DFMEA GR4 | 1.Make timing plan according to recooendation action and analysis list | 文本/Text |  | YES |  |  | -109W | -109W
|  | 2.RPN value redefine based on action and analysis list | 文本/Text |  | YES |  |  | -109W | -109W
|  | 3.Any new failure happen,need to update DFMEA. | 文本/Text |  | YES |  |  | -109W | -109W
|  | 4.Review and ensure some items which impact ME be transferred into PFMEA. | 文本/Text |  | YES |  |  | -109W | -109W
|  | 5.DRE should assure to initial the completed DFMEA/DRBFM analysis(does not include any columns under Action results heading) and pass approval process in GDM before GR4 deadline | 文本/Text |  | YES |  |  | -109W | -109W
|  | 6.SVE and EGM relative sign off persons in above approval process in GDM. | 文本/Text |  | YES |  |  | -109W | -109W
6 | Soft Tooling | 1.Timing review to check TKO is meeting program MRD | 文本/Text |  | YES |  |  | -104W | -104W
|  | 2.EWO/Open issue list review,ensure no items which impact TKO action still open | 文本/Text |  | YES |  |  | -104W | -104W
|  | 3.No further EWOs be in draft phase | 文本/Text |  | YES |  |  | -104W | -104W
|  | 4.Engineering design proposal review including drawing and math data,ensure they are meeting design requirement | 文本/Text |  | YES |  |  | -104W | -104W
|  | 5.any open issues in review meeting should list and follow up | 文本/Text |  | YES |  |  | -96W | -96W
|  | 6.Archiving the tooling check list into GDM | 文本/Text |  | YES |  |  | -96W | -96W
|  | 7.plan 1-2 visits to tooling supplier. | 文本/Text |  | YES |  |  | -104W | -96W
7 | IV Parts Check | 1.BOM check to ensure PO release with latest right part number.BCR release if temporary BOM change be needed. | 文本/Text | clearance check results | YES |  |  | -96W | -95W
|  | 2.Use quality checklist to inspect parts | 文本/Text |  | YES |  |  | -96W | -95W
8 | DV Test | 1.Test sample review,pre-test DRBTR check per check list template.Critical area of welding part check and mark with white paint | 文本/Text |  | YES |  |  | -96W | -96W
|  | 2.Test status tracking in PDT,any crack need to record and update every day | 文本/Text |  | YES |  |  | -96W | -88W
|  | 3.Regular visual inspect:metal and welding seam crack,oil leakage,abnormal noise | 文本/Text |  | YES |  |  | -88W | -88W
|  | 4Test result review | 文本/Text |  | YES |  |  | -88W | -88W
|  | 5.After test,do DRBTR work per template list,meanwhile test sample sealin until SORP+1year. | 文本/Text |  | YES |  |  | -88W | -88W
9 | IV MRD | 1.Ensure DV test finished before IV sample delivery | 文本/Text |  | YES |  |  | -88W | -88W
|  | 2.BOM check to ensure PO release with latest right part number if EWO happen.BCR release if temporary BOM change be needed | 文本/Text |  | YES |  |  | -88W | -88W
|  | 3.PPQP two weeks ahead of MRD,Review PPQP document,specially tier 2 or 3 supllier list,ensure dimension is meeting over 98% eligible rate. | 文本/Text |  | YES |  |  | -88W | -86W
|  | 4.Any retrofit,need BSD support and make archiving | 文本/Text |  | YES |  |  | -86W | -86W
|  | 5.Review build SIL,follow up open issue list | 文本/Text |  | YES |  |  | -78W | -78W
|  | 6.Archiving SIL into GDM. | 文本/Text |  | YES |  |  | -78W | -78W